## QA Executive Summary
PRORESUME STUDIO — QA TEST AUDIT & EXECUTIVE DASHBOARD
Application: React 18 + Vite + Tailwind CSS ¦ Target: http://localhost:3000 ¦ Cycle: 1.0 Full Regression & Defect Triage
1. TEST EXECUTION SUMMARY (KEY METRICS)
Total Test Cases | Passed | Failed | Blocked | Pass Rate (%) | Execution Status
85 | 69 | 12 | 4 | 81.2% | 100% COMPLETE
2. DEFECT SEVERITY DISTRIBUTION
Critical (P0) | High Severity (P1) | Medium Severity (P2) | Low Severity (P3) | Total Defects Logged | Blocker Impact
0 | 5 | 4 | 3 | 12 | HIGH (Release Blocker)
3. TEST EXECUTION BREAKDOWN BY APPLICATION MODULE
Module / Application Subsystem | Total Test Items | Passed | Failed | Pass Rate (%) | QA Evaluation & Status
Navigation & Landing Page | 8 | 8 | 0 | 100.0% | PASS - STABLE
Personal Details & Profile Photo | 10 | 8 | 2 | 80.0% | NEEDS ATTENTION (XSS / Link bug)
Professional Summary & Presets | 5 | 5 | 0 | 100.0% | PASS - STABLE
Work Experience & Achievements | 9 | 8 | 1 | 88.9% | NEEDS ATTENTION (Empty bullet)
Education History | 6 | 6 | 0 | 100.0% | PASS - STABLE
Skills & Proficiencies | 7 | 7 | 0 | 100.0% | PASS - STABLE
Projects & Portfolio Links | 7 | 5 | 2 | 71.4% | DEFECT DETECTED (GitHub URL missing)
Certifications & Licenses | 6 | 4 | 2 | 66.7% | DEFECT DETECTED (Credential ID missing)
Custom Sections | 6 | 5 | 1 | 83.3% | NEEDS ATTENTION (Empty header)
Design, Templates, Themes & Fonts | 8 | 8 | 0 | 100.0% | PASS - STABLE
Presets & JSON Backup / Restore | 7 | 5 | 2 | 71.4% | DEFECT DETECTED (Import crash)
PDF Print Engine & Responsiveness | 6 | 2 | 4 | 33.3% | CRITICAL FIXES REQUIRED (Print bugs)
4. FORMAL QA SIGN-OFF DECISION & RECOMMENDATION
RELEASE DECISION: CONDITIONAL REJECTION FOR PRODUCTION DEPLOYMENT QA AUDIT ASSESSMENT: The ProResume Studio interactive application demonstrates high quality in component reactivity, client-side data persistence, real-time typography/palette switches, and responsive UI controls. However, 5 HIGH-severity defects prevent production release: 1. [BUG-001] The left editor panel is printed alongside the resume in PDF output (editor not hidden). 2. [BUG-002] Interactive zoom scale distorts the print layout (zooming out to 50% produces a tiny shrunken PDF). 3. [BUG-003] Mobile users attempting to "Download PDF" while in Edit mode receive a 100% BLANK page. 4. [BUG-004] Project GitHub repository URLs and Certification Credential IDs entered by users are completely omitted in all 4 resume templates. 5. [BUG-005] Uploading an incomplete or malformed JSON resume crashes the React application with a White Screen of Death. RECOMMENDED ACTION: Execute developer fixes outlined in Sheet "Developer Debugging Guide". Estimated remediation time: 1 developer day.

## Test Cases Matrix
Test Case ID | Module | Feature / Component | Test Scenario & Objective | Preconditions | Test Steps | Expected Result | Actual Result | Status | Severity / Priority | Linked Defect
TC-NAV-01 | Navigation | Landing Page | Verify Landing page loads correctly at root URL | App running on localhost:3000 | 1. Open browser 2. Navigate to http://localhost:3000 | Landing page displays hero title, mockup, feature cards, template showcase. | Landing page renders properly with responsive layout. | Pass | P1 - High
TC-NAV-02 | Navigation | Landing to Builder | Click "Launch Builder" button in header | On landing page | 1. Click "Launch Builder" button | View transitions to builder workspace; URL hash changes to #builder | Transitions smoothly, hash set to #builder | Pass | P1 - High
TC-NAV-03 | Navigation | Landing to Builder | Click "Build My Resume Now" hero CTA | On landing page | 1. Click hero CTA button | Transitions directly to builder workspace | Transitions to builder workspace | Pass | P1 - High
TC-NAV-04 | Navigation | Template Showcase | Click "Select Template" on Modern card | On landing page #templates | 1. Scroll to templates 2. Click "Select Template" on Modern Tech card | Opens builder with Modern template preselected | Opens builder with Modern template selected | Pass | P2 - Medium
TC-NAV-05 | Navigation | Template Showcase | Click "Select Template" on Classic card | On landing page | 1. Click "Select Template" on Classic Serif card | Opens builder with Classic template preselected | Opens builder with Classic template selected | Pass | P2 - Medium
TC-NAV-06 | Navigation | Template Showcase | Click "Select Template" on Minimalist card | On landing page | 1. Click "Select Template" on Minimalist ATS card | Opens builder with Minimalist template preselected | Opens builder with Minimalist template selected | Pass | P2 - Medium
TC-NAV-07 | Navigation | Template Showcase | Click "Select Template" on Executive card | On landing page | 1. Click "Select Template" on Executive Sidebar card | Opens builder with Executive template preselected | Opens builder with Executive template selected | Pass | P2 - Medium
TC-NAV-08 | Navigation | Builder Back Navigation | Click "Home" button in builder top navbar | In builder workspace | 1. Click "Home" button with ArrowLeft icon | Returns to landing page view, clears #builder hash | Returns to landing page, hash cleared | Pass | P2 - Medium
TC-PER-01 | Personal Details | Text Inputs | Update Full Name field and verify live preview | Personal tab active | 1. Type "Sarah Connor" in Full Name | Resume header updates instantly to "Sarah Connor" | Header updates in real-time across all templates | Pass | P1 - High
TC-PER-02 | Personal Details | Text Inputs | Update Headline / Target Role | Personal tab active | 1. Type "Lead Cloud Security Engineer" | Sub-headline reflects updated text immediately | Sub-headline updates immediately | Pass | P2 - Medium
TC-PER-03 | Personal Details | Contact Inputs | Enter Email, Phone, and Location | Personal tab active | 1. Fill valid email, phone, and city | Contact info appears with correct icons in preview | Contact info displays properly | Pass | P2 - Medium
TC-PER-04 | Personal Details | URL Formatter | Enter portfolio, linkedin, github URLs | Personal tab active | 1. Type https://linkedin.com/in/sarah 2. Type https://github.com/sarah | formatUrl cleans protocol for clean visual display, link href points to URL | Visual text cleans protocol; link href points to URL | Pass | P2 - Medium
TC-PER-05 | Personal Details | Photo Upload | Upload local JPG file via file picker | Personal tab active | 1. Click "Upload Photo from PC" 2. Choose a 2MB JPEG image | Image is downscaled on canvas (max 400x400) and displays in thumbnail & preview | Image compressed to data URL and renders in preview | Pass | P2 - Medium
TC-PER-06 | Personal Details | Photo Drag & Drop | Drag & drop image file onto dropzone | Personal tab active | 1. Drag JPG onto dropzone box 2. Release mouse button | Dropzone highlights green; file is parsed and displayed | Drag over styling works, image parsed properly | Pass | P2 - Medium
TC-PER-07 | Personal Details | Photo Validation | Upload invalid file type (e.g. PDF or TXT) | Personal tab active | 1. Drag or select a .pdf file | Displays error: "Please choose an image file (JPEG, PNG, WEBP, etc.)" | Error banner appears correctly | Pass | P2 - Medium
TC-PER-08 | Personal Details | Photo Toggle | Toggle "Show on Resume" checkbox | Profile photo present | 1. Uncheck "Show on Resume" | Photo is hidden from resume preview; thumbnail preserved in editor | Photo hides on resume preview | Pass | P2 - Medium
TC-PER-09 | Personal Details | Photo Removal | Click "Remove" photo button | Profile photo present | 1. Click "Remove" button | Photo cleared from editor and resume template | Photo successfully removed | Pass | P2 - Medium
TC-PER-10 | Personal Details | Security - XSS in Links | Input "javascript:alert(1)" in website/linkedin | Personal tab active | 1. In Portfolio field, enter "javascript:alert(1)" 2. Click the link in resume preview | Link should be sanitized/blocked or inert | Link renders raw href="javascript:alert(1)" allowing script execution on click | Fail | P1 - High | BUG-007
TC-SUM-01 | Summary | Textarea Input | Type multi-paragraph summary text | Summary tab active | 1. Enter 300 characters of professional background | Live preview updates text immediately with justified alignment | Updates in real-time with justified alignment | Pass | P2 - Medium
TC-SUM-02 | Summary | Character Counter | Verify character count increments dynamically | Summary tab active | 1. Type characters and verify top-right badge | Counter displays accurate character length | Character count is accurate | Pass | P3 - Low
TC-SUM-03 | Summary | Preset Loader | Click "Load Tech / Engineering" inspiration preset | Summary tab active | 1. Click "Load Tech / Engineering" button | Textarea replaces text with engineering summary template | Textarea populates with tech template | Pass | P3 - Low
TC-SUM-04 | Summary | Preset Loader | Click "Load Product / Management" preset | Summary tab active | 1. Click "Load Product / Management" | Populates with PM summary template | Populates correctly | Pass | P3 - Low
TC-SUM-05 | Summary | Preset Loader | Click "Load Data / AI Specialist" preset | Summary tab active | 1. Click "Load Data / AI Specialist" | Populates with AI specialist summary template | Populates correctly | Pass | P3 - Low
TC-EXP-01 | Experience | Add Experience | Click "+ Add Role" button | Experience tab active | 1. Click "+ Add Role" | New experience item card added with default fields and blank bullet | Card added with generated timestamp ID | Pass | P1 - High
TC-EXP-02 | Experience | Edit Role Fields | Fill Role, Company, Location, Start Date, End Date | Experience card exists | 1. Enter "Staff Engineer", "Google", "Mountain View, CA", "2020-01", "2023-08" | Preview displays formatted dates "Jan 2020 – Aug 2023" and role title | Dates formatted nicely, role and company displayed | Pass | P1 - High
TC-EXP-03 | Experience | Current Job Toggle | Check "I currently work here" | Experience card exists | 1. Check "I currently work here" | End date input is disabled, displays "Present"; preview shows "Jan 2020 – Present" | End date disabled, shows Present | Pass | P2 - Medium
TC-EXP-04 | Experience | Reorder Positions | Click "Move Down" (ChevronDown) on position #1 | At least 2 experience items exist | 1. Click Down arrow on top item | Item switches position with item #2; preview order updates | Array items swapped, preview reordered | Pass | P2 - Medium
TC-EXP-05 | Experience | Reorder Boundaries | Verify Move Up disabled on first item, Move Down disabled on last item | Multiple experience items | 1. Observe top item Move Up button 2. Observe bottom item Move Down button | Disabled state with opacity-30 and cursor-not-allowed | Buttons correctly disabled at boundaries | Pass | P3 - Low
TC-EXP-06 | Experience | Add Bullet Point | Click "+ Add Bullet" in experience item | Experience item exists | 1. Click "+ Add Bullet" | New bullet textarea row appears | New textarea added to highlights array | Pass | P2 - Medium
TC-EXP-07 | Experience | Remove Bullet Point | Click trash icon next to bullet point | Multiple bullets exist | 1. Click trash icon on bullet #2 | Bullet #2 is deleted from list and preview | Bullet removed successfully | Pass | P2 - Medium
TC-EXP-08 | Experience | Remove Experience | Click trash icon in card header | Experience item exists | 1. Click trash icon in card header | Entire experience card deleted; preview removes section entry | Card deleted, preview updated | Pass | P2 - Medium
TC-EXP-09 | Experience | Empty Bullet Render | Add bullet point but leave text empty | Experience item exists | 1. Click "+ Add Bullet" 2. Leave textarea empty 3. Check preview | Empty bullet should NOT render an orphan bullet dot on resume | Renders an empty <li></li> with visible bullet dot on resume | Fail | P2 - Medium | BUG-008
TC-EDU-01 | Education | Add Degree | Click "+ Add Degree" | Education tab active | 1. Click "+ Add Degree" | New education card created with empty inputs | Card created with default fields | Pass | P1 - High
TC-EDU-02 | Education | Edit Degree Fields | Fill Degree, Institution, Major, Dates, GPA | Education card exists | 1. Enter "M.S.", "MIT", "Computer Science", "2018", "2020", "GPA 4.0" | Preview displays all details in education block | Renders correctly with institution and honors | Pass | P1 - High
TC-EDU-03 | Education | Remove Degree | Click trash icon on education item | Education card exists | 1. Click trash icon | Education item removed; preview updates | Item removed from array and view | Pass | P2 - Medium
TC-EDU-04 | Education | Empty State | Delete all education items | No education items | 1. Delete all items | Editor displays empty placeholder; template hides Education section | Placeholder shown, section hidden in template | Pass | P2 - Medium
TC-EDU-05 | Education | Date Formatting | Enter graduation year "2022" vs "2022-05" | Education card exists | 1. Enter "2022-05" in graduation date | Formats as "May 2022" in preview | Formatted as "May 2022" | Pass | P3 - Low
TC-EDU-06 | Education | Honors / Score | Enter GPA with honors text | Education card exists | 1. Enter "GPA: 3.95 (Summa Cum Laude)" | Displays cleanly under institution name | Displays correctly | Pass | P3 - Low
TC-SKL-01 | Skills | Add Category | Click "+ Add Category" | Skills tab active | 1. Click "+ Add Category" | Creates category card with default name "New Skill Category" | Category card created | Pass | P2 - Medium
TC-SKL-02 | Skills | Rename Category | Edit category title input | Skills category exists | 1. Change text to "DevOps & Cloud" | Category name updates in editor and template header | Updates dynamically | Pass | P2 - Medium
TC-SKL-03 | Skills | Add Skill Single | Type skill name and press Enter | Category exists | 1. Type "Docker" 2. Press Enter | Skill added as pill tag; input cleared | Skill tag added, input cleared | Pass | P2 - Medium
TC-SKL-04 | Skills | Add Skills Comma-Separated | Type "Kubernetes, Terraform, Ansible" and click Add | Category exists | 1. Type comma-separated list 2. Click "Add" | Splits by comma, trims whitespace, adds 3 separate tags | Adds 3 separate pill tags | Pass | P2 - Medium
TC-SKL-05 | Skills | Duplicate Prevention | Add duplicate skill tag to same category | Category has "Docker" | 1. Type "Docker" again 2. Click "Add" | Duplicate ignored; Set prevents duplicate items | Set prevents duplicate addition | Pass | P3 - Low
TC-SKL-06 | Skills | Remove Skill Pill | Click "X" on skill pill tag | Skill pill exists | 1. Click "X" icon on "Docker" | Tag removed from category; preview updates | Tag removed | Pass | P2 - Medium
TC-SKL-07 | Skills | Remove Category | Click trash icon on category card | Category exists | 1. Click trash icon | Entire category and its items removed | Category deleted | Pass | P2 - Medium
TC-PRJ-01 | Projects | Add Project | Click "+ Add Project" | Projects tab active | 1. Click "+ Add Project" | New project card added with Name, Tech Stack, URLs, Description | Project card created | Pass | P1 - High
TC-PRJ-02 | Projects | Edit Project Info | Fill Name, Technologies, Description | Project card exists | 1. Enter project details | Details appear in preview project card | Details appear properly | Pass | P1 - High
TC-PRJ-03 | Projects | Live URL | Add Live URL to project | Project card exists | 1. Enter "https://myapp.dev" in Live URL | External link icon renders in project header with valid href | External link icon renders with href | Pass | P2 - Medium
TC-PRJ-04 | Projects | GitHub URL Display | Add Repository / GitHub Link to project and check template | Project card exists | 1. Enter "https://github.com/user/project" in Repository / GitHub Link 2. Inspect all 4 resume templates | GitHub link or repository icon should be displayed on resume | GitHub URL is COMPLETELY OMITTED in all 4 resume templates! Only link is rendered. | Fail | P1 - High | BUG-004
TC-PRJ-05 | Projects | Remove Project | Click trash icon on project card | Project card exists | 1. Click trash icon | Project card removed; preview updates | Project removed | Pass | P2 - Medium
TC-PRJ-06 | Projects | Empty Stack | Leave technologies empty in project | Project card exists | 1. Clear technologies field | Project renders name and description cleanly without empty brackets | Renders cleanly | Pass | P3 - Low
TC-PRJ-07 | Projects | Special Characters | Enter ampersands and brackets in project title | Project card exists | 1. Type "A & B [System Tool]" | Escapes cleanly without HTML entities glitch | Displays properly | Pass | P3 - Low
TC-CRT-01 | Certifications | Add Certification | Click "+ Add Certification" | Certifications tab active | 1. Click "+ Add Certification" | New certification card added | Card added | Pass | P2 - Medium
TC-CRT-02 | Certifications | Edit Certification | Fill Name, Issuer, Date | Cert card exists | 1. Enter "AWS Solutions Architect", "Amazon", "2023" | Preview displays certification name and issuer | Renders in preview | Pass | P2 - Medium
TC-CRT-03 | Certifications | Credential ID Display | Fill Credential ID in Certifications editor and inspect resume | Cert card exists | 1. Enter "AWS-PSA-994821" in Credential ID field 2. Inspect resume preview in all templates | Credential ID should display next to or below issuer | Credential ID is NEVER displayed in Modern, Classic, Minimalist, or Executive templates! | Fail | P1 - High | BUG-004
TC-CRT-04 | Certifications | Remove Certification | Click trash icon on cert card | Cert card exists | 1. Click trash icon | Certification removed from list | Removed successfully | Pass | P2 - Medium
TC-CRT-05 | Certifications | Verification URL | Enter verification link in certification | Cert card exists | 1. Enter link URL | Link should be accessible on resume | Link omitted in templates | Fail | P2 - Medium | BUG-004
TC-CRT-06 | Certifications | Empty Cert State | Delete all certifications | No certs in list | 1. Delete all cert cards | Certifications section hidden from resume templates | Section hidden cleanly | Pass | P3 - Low
TC-CST-01 | Custom Sections | Add Section | Click "+ Add Section" | Custom tab active | 1. Click "+ Add Section" | New section created titled "Custom Section" with 1 blank item | Section created with item | Pass | P2 - Medium
TC-CST-02 | Custom Sections | Edit Section Title | Rename section title to "Publications" | Custom section exists | 1. Change title to "Publications" | Header in preview updates to "Publications" | Header updates | Pass | P2 - Medium
TC-CST-03 | Custom Sections | Add Item to Section | Click "+ Add Entry" inside custom section | Custom section exists | 1. Click "+ Add Entry" | New item added to that section | New item row added | Pass | P2 - Medium
TC-CST-04 | Custom Sections | Empty Items Behavior | Delete all items within custom section | Custom section has items | 1. Delete all items in custom section 2. Inspect preview | Section header should NOT display if it has 0 items | Section header "Custom Section" still displays with empty blank space | Fail | P3 - Low | BUG-010
TC-CST-05 | Custom Sections | Delete Section | Click trash icon on section card | Custom section exists | 1. Click trash icon on section header | Entire section and its entries removed | Section removed | Pass | P2 - Medium
TC-CST-06 | Custom Sections | Multiple Sections | Add 2 custom sections (e.g. Languages & Volunteering) | Custom tab active | 1. Add Languages section 2. Add Volunteering section | Both render as independent sections on resume | Renders both sections sequentially | Pass | P2 - Medium
TC-DSG-01 | Design & Style | Template Switcher | Switch between Modern, Classic, Minimalist, Executive | Design & Style tab active | 1. Click each template card in turn | Preview changes layout immediately with zero data loss | Layout updates seamlessly across all 4 templates | Pass | P1 - High
TC-DSG-02 | Design & Style | Minimalist Single Name | Enter single-word name (e.g. "Cher") in Minimalist template | Minimalist template active | 1. Set Full Name to "Cher" 2. Inspect Minimalist header | Header displays "Cher" | Header displays "Cher Name" due to split/join fallback bug | Fail | P2 - Medium | BUG-006
TC-DSG-03 | Design & Style | Classic Separator Dots | Leave phone/location empty, provide LinkedIn in Classic template | Classic template active | 1. Clear phone & location 2. Fill LinkedIn URL | Header renders "LinkedIn" without leading orphan bullet | Header renders orphan bullet "• LinkedIn" | Fail | P2 - Medium | BUG-009
TC-DSG-04 | Design & Style | Color Palettes | Select Emerald, Amber, Charcoal, Ruby, Teal, Terracotta | Design tab active | 1. Click each color palette button | Primary, secondary, and accent colors update across headers and borders | Colors update dynamically across templates | Pass | P2 - Medium
TC-DSG-05 | Design & Style | Typography Fonts | Select Sans (Inter), Serif (Merriweather), Display (Poppins) | Design tab active | 1. Click each font option | Font family class applied to preview container (.font-sans, .font-serif, .font-display) | Font classes applied properly | Pass | P2 - Medium
TC-DSG-06 | Design & Style | Zoom Controls | Test Zoom In (+10%), Zoom Out (-10%), and Reset (85%) | Builder preview active | 1. Click Zoom In 2. Click Zoom Out 3. Click Maximize (Reset) | Scale changes smoothly from 50% to 130%; Reset restores 85% | Scale transforms as expected in viewport | Pass | P2 - Medium
TC-DSG-07 | Design & Style | Executive Sidebar Dual Column | Switch to Executive template and inspect 2-column grid | Executive template active | 1. Switch to Executive template | Left 36% sidebar with avatar/contact/skills; Right 64% main experience column | Renders two distinct columns | Pass | P2 - Medium
TC-DSG-08 | Design & Style | Palette Reset on Indigo | Load old deprecated palette "indigo" | LocalStorage contains indigo theme | 1. Check App.jsx initial theme state logic | Detects deprecated id and safely resets to Emerald | Resets to Emerald palette safely | Pass | P3 - Low
TC-DAT-01 | Data Management | Auto-Save | Edit field and verify localStorage persistence | Builder active | 1. Edit Full Name 2. Wait 1 sec 3. Refresh browser (F5) | "Auto-saved" badge flickers; refreshed page retains edited name | Data persists in localStorage key proresume_data_v1 | Pass | P1 - High
TC-DAT-02 | Data Management | Presets Menu | Load "Software Engineer (Demo)" preset | Sample Presets menu open | 1. Click "Software Engineer (Demo)" | Resume data replaces with Alexander Wright sample data | Preset loaded successfully | Pass | P2 - Medium
TC-DAT-03 | Data Management | Presets Menu | Load "Product Manager (Demo)" preset | Sample Presets menu open | 1. Click "Product Manager (Demo)" | Resume data replaces with Elena Rostova sample data | Preset loaded successfully | Pass | P2 - Medium
TC-DAT-04 | Data Management | Presets Menu | Load "Clear / Blank Canvas" preset | Sample Presets menu open | 1. Click "Clear / Blank Canvas" | All form fields cleared for fresh resume build | All fields emptied cleanly | Pass | P2 - Medium
TC-DAT-05 | Data Management | JSON Export | Click "JSON" export button | Builder active with data | 1. Click JSON download button in header | Downloads file named "<name>_backup.json" with schema version, template, theme, font, resumeData | JSON file downloaded with expected schema | Pass | P1 - High
TC-DAT-06 | Data Management | JSON Import Valid | Import previously exported backup JSON | Valid JSON backup on disk | 1. Click "Import" 2. Select exported JSON file | Resume data, template, theme, and font restored accurately | State restored accurately | Pass | P1 - High
TC-DAT-07 | Data Management | JSON Import Malformed | Import invalid JSON or non-resume JSON (e.g. {"foo": 123}) | Malformed file ready | 1. Click "Import" 2. Select malformed JSON file | Validation catches invalid schema, displays alert, prevents app crash | Crash: setResumeData sets incomplete object; components call .map() on undefined and White Screen occurs | Fail | P1 - High | BUG-005
TC-DAT-08 | Data Management | Storage Quota | Upload multiple very large high-res images exceeding 5MB localStorage | Large image files | 1. Upload large uncompressed base64 images 2. Trigger save | If quota exceeded, alert user with storage warning | Catches error and logs console.error silently without notifying user | Fail | P3 - Low | BUG-011
TC-PRN-01 | Print & PDF Export | Download PDF Action | Click "Download PDF" button in header | Builder active | 1. Click "Download PDF" | Sets document title to candidate name, opens window.print() dialog | Sets title and opens print dialog | Pass | P1 - High
TC-PRN-02 | Print & PDF Export | Print CSS Visibility | Inspect print preview for presence of Editor panel | Desktop browser | 1. Press Ctrl+P or click Download PDF 2. Inspect print preview stream | Only the resume page (.a4-page) should be visible; all editor inputs hidden | FAIL: Editor form panel is NOT hidden in print CSS! Prints inputs & buttons alongside resume | Fail | P1 - High | BUG-001
TC-PRN-03 | Print & PDF Export | Print Zoom Scaling | Change Zoom to 50% and click Download PDF | Zoom set to 50% | 1. Set Zoom to 50% 2. Click "Download PDF" | Print output must print at exact 100% scale regardless of viewport preview zoom | FAIL: Inline transform: scale(0.5) overrides print CSS; printed resume is tiny at 50% scale! | Fail | P1 - High | BUG-002
TC-PRN-04 | Print & PDF Export | Mobile Print Mode | On mobile screen (<768px), click Download PDF while on "Edit" tab | Viewport width < 768px, mobileMode === "edit" | 1. Switch to mobile viewport (375px) 2. Ensure "Edit" icon is selected 3. Click Download PDF | Resume prints normally regardless of mobile active view | FAIL: In "edit" mode, preview div has "hidden" (display: none). Prints a completely BLANK page! | Fail | P1 - High | BUG-003
TC-PRN-05 | Print & PDF Export | Document Title Restore | Check PDF suggested save filename in print dialog | Candidate name set | 1. Click Download PDF 2. Observe suggested PDF filename in save dialog | Suggested filename equals "<FullName> - CV.pdf" | Document title restored immediately after window.print() causing race condition in Chromium | Fail | P3 - Low | BUG-012

## Defect Log & Bug Tracker
Defect ID | Severity | Priority | Module | Defect Title | Steps to Reproduce | Expected Behavior | Actual Behavior | Root Cause Analysis | Fix Recommendation | Status
BUG-001 | High | P1 - High | PDF Print Engine | Editor form panel is printed alongside resume in PDF output | 1. Launch builder on desktop screen (width >= 768px) 2. Click "Download PDF" button in header 3. Inspect the print preview dialog | Only the resume sheet (.a4-page) should be sent to print output. Editor form panel must be completely hidden. | The left editor panel (with inputs, tabs, buttons) is included in the print stream, breaking page layout. | In App.jsx, the left column container <div className="w-full md:w-1/2 lg:w-5/12..."> lacks the "no-print" CSS class. Only the top header, tabs, and preview toolbar have "no-print". | Add "no-print" to the left editor container in App.jsx (e.g. className="no-print w-full md:w-1/2..."). Also ensure ".no-print { display: none !important; }" is declared in index.css. | Open
BUG-002 | High | P1 - High | PDF Print Engine | Preview zoom scale persists in print output causing shrunken PDF resumes | 1. In builder preview toolbar, click Zoom Out until zoom is 50% or 70% 2. Click "Download PDF" 3. Observe print preview layout | Printed resume must always render at exact 100% scale (A4: 210mm x 297mm) regardless of interactive preview zoom. | Inline style transform: scale(0.5) is not overridden by @media print. Resume prints at 50% miniature size with massive blank margins. | In App.jsx line 492, inline style style={{ transform: `scale(${zoom / 100})` }} is applied to the direct parent of the template. In index.css, @media print resets .print-area transform, but NOT the child element with inline scale. | In index.css @media print, add rule: ".print-area > div { transform: none !important; transform-origin: unset !important; }". | Open
BUG-003 | High | P1 - High | Mobile Responsiveness | "Download PDF" prints blank document when invoked from Mobile "Edit" mode | 1. Resize browser to mobile size (e.g. 375px) or open on phone 2. Ensure default "Edit" tab is active in mobile toggle 3. Click "Download PDF" in header | Resume document prints cleanly on mobile devices. | A blank page is printed! When mobileMode is "edit", the preview wrapper has the CSS class "hidden" (display: none), completely hiding the print area. | In App.jsx line 445: className={`w-full md:w-1/2 lg:w-7/12 ... ${mobileMode === "edit" ? "hidden md:flex" : "flex"}`}. During window.print(), display: none is not overridden. | In index.css @media print, add: ".print-area, .print-area * { display: block !important; } and ensure the right preview container has print:flex or print:block override. | Open
BUG-004 | High | P1 - High | Templates & Data | Project GitHub URLs and Certification Credential IDs entered in editor are omitted in all templates | 1. Add a project with both Live Link and GitHub Link (e.g. https://github.com/myname/proj) 2. Add a certification with Credential ID "AWS-9948" 3. Check Modern, Classic, Minimalist, and Executive templates | Entered GitHub links should display (with GitHub icon or text) and Credential ID should display next to certification issuer. | Neither GitHub URLs nor Credential IDs are rendered anywhere in any of the 4 resume templates! Data entered by user is completely lost from resume. | In ModernTemplate.jsx, ClassicTemplate.jsx, MinimalistTemplate.jsx, and ExecutiveTemplate.jsx, JSX only references proj.link (ignoring proj.github) and cert.issuer/date (ignoring cert.credentialId). | Update all 4 template JSX files to render proj.github with GitHub icon/link, and render cert.credentialId when present. | Open
BUG-005 | High | P1 - High | Data Management | Importing malformed or incomplete JSON crashes entire React application (White Screen) | 1. Click "Import" in header 2. Select a JSON file missing some keys (e.g. {"name": "Test"} or empty JSON {}) 3. Observe UI | System validates schema. If invalid, displays error alert and retains existing state safely. | React crashes with unhandled TypeError: Cannot read properties of undefined (reading "map") in ExperienceEditor / SkillsEditor. Page turns completely blank. | In App.jsx handleImportJSON: parsed object is directly passed to setResumeData(parsed) without merging default fallback keys from initialResumeData or blank preset. | Deep-merge imported object with initialResumeData defaults: setResumeData({ ...blankPreset, ...parsed, personal: { ...blankPreset.personal, ...parsed.personal } }). | Open
BUG-006 | Medium | P2 - Medium | Minimalist Template | Single-word / Mononym Full Name (e.g. "Cher") renders "Cher Name" in Minimalist template | 1. Switch to Minimalist template in Design tab 2. In Personal Details, set Full Name to "Cher" (single word) 3. Check header in Minimalist preview | Header displays "Cher". | Header displays "Cher Name"! The slice(1).join(" ") evaluates to "" which triggers the fallback "Name". | In MinimalistTemplate.jsx line 14: {personal.fullName?.split(" ").slice(1).join(" ") ¦¦ "Name"}. When there is no second word, join(" ") is empty string, which is falsy. | Check if name array has more than 1 word before falling back: const parts = (personal.fullName ¦¦ "").trim().split(/\s+/); const firstName = parts[0] ¦¦ "Your"; const lastName = parts.slice(1).join(" ") ¦¦ (parts.length > 1 ? "" : ""); | Open
BUG-007 | Medium | P2 - Medium | Security & Links | Unsanitized URLs permit javascript: execution and relative URL 404s for URLs lacking protocol | 1. In Portfolio field, enter "javascript:alert(document.domain)" or "linkedin.com/in/user" (without https://) 2. Click the link in resume preview | Protocol-less URLs should auto-prepend "https://"; "javascript:" URLs must be sanitized to "#" or rejected. | Clicking javascript: executes script. Clicking linkedin.com/in/user navigates to http://localhost:3000/linkedin.com/in/user (404 error). | href attributes in templates render raw user string without prefixing https:// or stripping javascript: protocol. | Create a safeUrl(url) helper in formatters.js: if (/^javascript:/i.test(url)) return "#"; return url.startsWith("http") ? url : "https://" + url; | Open
BUG-008 | Medium | P2 - Medium | Experience Editor | Blank bullet points in Work Experience render empty orphan bullet dots in resume preview | 1. In Work Experience, click "+ Add Bullet" 2. Leave textarea completely empty 3. Check resume preview in Modern/Classic/Executive templates | Empty or whitespace-only bullets should be filtered out from resume preview rendering. | A visible bullet dot "• " renders with no accompanying text, degrading resume professionalism. | Templates directly map over highlights: exp.highlights.map((h, i) => <li key={i}>{h}</li>) without checking if h.trim().length > 0. | Filter highlights in templates: exp.highlights.filter(h => h && h.trim().length > 0).map(...) | Open
BUG-009 | Medium | P2 - Medium | Classic Template | Classic Template displays orphan separator bullet "•" when initial contact fields are omitted | 1. Switch to Classic template 2. Clear Phone, Location, and Email fields 3. Enter LinkedIn URL | LinkedIn appears cleanly without a preceding separator bullet. | Header renders "• LinkedIn" with an orphan leading separator dot. | In ClassicTemplate.jsx lines 43-48: {personal.linkedin && <span>•</span>} is rendered unconditionally if linkedin is truthy, regardless of whether preceding items exist. | Store active contact items in an array and render using array join or flex gap instead of hardcoded conditional dots. | Open
BUG-010 | Low | P3 - Low | Custom Sections | Custom Section headers remain visible when all child entries are removed | 1. Add a Custom Section titled "Volunteering" 2. Delete the item inside it so items array is empty 3. Check resume preview | Empty custom section with 0 items should not render header on the resume. | Section title "Volunteering" renders with empty blank whitespace beneath it. | Templates check customSections.map(sec => <section key={sec.id}><h2>{sec.title}</h2>... without verifying sec.items && sec.items.length > 0. | In templates, add guard: {sec.items && sec.items.length > 0 && <section>...</section>} | Open
BUG-011 | Low | P3 - Low | Local Storage | LocalStorage QuotaExceededError when uploading large images fails silently without user alert | 1. Upload multiple high-resolution images or paste long base64 strings into avatar 2. Exceed 5MB localStorage browser quota | User should see a banner or toast: "Storage quota exceeded. Image may not persist after page refresh." | Silent console.error("Storage error:", err); user is unaware changes are not being persisted. | Catch block in App.jsx only logs to console: catch (err) { console.error("Storage error:", err); }. | Set a state variable storageError and render a warning notification banner if quota is exceeded. | Open
BUG-012 | Low | P3 - Low | Print Engine | Document title for printed PDF file name race condition on Chromium print spooler | 1. In App.jsx handlePrint(), document.title is modified immediately before window.print() and reset immediately after 2. Test on Chromium/Edge print dialog | PDF file name defaults reliably to candidate name in print dialog. | On some Chromium versions where window.print() is non-blocking, title resets back to "ProResume Studio" before print spooler reads it. | document.title = originalTitle is executed synchronously in the same call stack. | Use setTimeout(() => { document.title = originalTitle; }, 1000) or listen to window.onafterprint event. | Open

## Developer Debugging Guide
Defect ID | Target File Path | Line Numbers | Defect Description | Exact Code Fix Snippet (Copy-Paste Ready) | Verification Instructions
BUG-001 | src/App.jsx & src/index.css | App.jsx: 351-355 | Hide Left Editor panel during print | // In src/App.jsx line 351: <div className={`no-print w-full md:w-1/2 lg:w-5/12 flex flex-col border-r border-zinc-800 bg-zinc-950 ${ mobileMode === "preview" ? "hidden md:flex" : "flex" `}> // In src/index.css @media print: @media print { .no-print { display: none !important; } } | Verify by pressing Ctrl+P. Only the white resume sheet must appear in print preview.
BUG-002 | src/index.css | index.css: 50-57 | Reset Preview Zoom scale in Print media query | // In src/index.css line 50, update @media print: .print-area { margin: 0 !important; padding: 0 !important; width: 100% !important; background: transparent !important; box-shadow: none !important; } .print-area > div { transform: none !important; transform-origin: unset !important; } | Set preview zoom to 50%, then print. Verify document prints at full 100% A4 size.
BUG-003 | src/index.css | index.css: 38-71 | Force preview visibility during mobile print | // In src/index.css @media print: @media print { /* Ensure preview column is never hidden by mobileMode class */ .print-area, div[class*="w-full md:w-1/2 lg:w-7/12"] { display: flex !important; width: 100% !important; } } | Test on phone or responsive mode 375px in "Edit" tab. Click Download PDF and confirm preview is printed.
BUG-004 | src/components/templates/*.jsx | All 4 templates | Render proj.github and cert.credentialId in templates | // In Projects section: {proj.github && ( <a href={proj.github} target="_blank" rel="noreferrer" title="GitHub Repository" className="hover:underline flex items-center gap-1 text-[11px] text-slate-500"> <Github className="w-3 h-3" /> Code </a> )} // In Certifications section: {cert.credentialId && <span className="text-slate-400 text-[10px] ml-1">(ID: {cert.credentialId})</span>} | Verify both GitHub links and Credential IDs appear across Modern, Classic, Minimalist, Executive templates.
BUG-005 | src/App.jsx | App.jsx: 167-188 | Safe JSON Import with Schema Validation & Fallback Defaults | const handleImportJSON = (e) => { const file = e.target.files?.[0]; if (!file) return; const reader = new FileReader(); reader.onload = (event) => { try { const parsed = JSON.parse(event.target.result); const rawData = parsed.resumeData ¦¦ parsed; if (!rawData ¦¦ typeof rawData !== "object") throw new Error("Invalid format"); const sanitized = { personal: { ...initialResumeData.personal, ...(rawData.personal ¦¦ {}) }, summary: rawData.summary ¦¦ "", experience: Array.isArray(rawData.experience) ? rawData.experience : [], education: Array.isArray(rawData.education) ? rawData.education : [], skills: Array.isArray(rawData.skills) ? rawData.skills : [], projects: Array.isArray(rawData.projects) ? rawData.projects : [], certifications: Array.isArray(rawData.certifications) ? rawData.certifications : [], customSections: Array.isArray(rawData.customSections) ? rawData.customSections : [] }; setResumeData(sanitized); if (parsed.template) setTemplate(parsed.template); if (parsed.theme) setTheme(parsed.theme); if (parsed.fontFamily) setFontFamily(parsed.fontFamily); } catch (err) { alert("Invalid JSON resume file format. Please upload a valid export."); } }; reader.readAsText(file); e.target.value = ""; }; | Test importing {"test":123} or empty file. Verify alert appears and app does NOT crash.
BUG-006 | src/components/templates/MinimalistTemplate.jsx | MinimalistTemplate.jsx: 11-15 | Fix Single-word / Mononym Full Name rendering "Cher Name" | const fullName = (personal.fullName ¦¦ "").trim(); const nameParts = fullName ? fullName.split(/\s+/) : ["Your", "Name"]; const firstName = nameParts[0]; const restOfName = nameParts.length > 1 ? nameParts.slice(1).join(" ") : ""; // In JSX: <h1 className="text-3xl font-light tracking-tight text-slate-900"> <span className="font-bold">{firstName}</span> {restOfName} </h1> | Type "Cher" or "Alexander". Verify name displays as "Cher" rather than "Cher Name".
BUG-007 | src/utils/formatters.js | formatters.js: 18-22 | URL Sanitization & Protocol Auto-Prepender | export function sanitizeUrl(url) { if (!url) return ""; const trimmed = url.trim(); if (/^javascript:/i.test(trimmed)) return "#"; if (/^https?:\/\//i.test(trimmed) ¦¦ /^mailto:/i.test(trimmed) ¦¦ /^tel:/i.test(trimmed)) { return trimmed; } return `https://${trimmed}`; } | Use sanitizeUrl for all href={...} attributes across templates.
BUG-008 | src/components/templates/*.jsx | Work Experience section | Filter out empty bullet highlights before mapping | {exp.highlights && exp.highlights.filter(h => h && h.trim().length > 0).length > 0 && ( <ul className="list-disc list-outside ml-4 text-xs sm:text-sm text-slate-700 space-y-1"> {exp.highlights.filter(h => h && h.trim().length > 0).map((h, i) => ( <li key={i}>{h}</li> ))} </ul> )} | Add empty bullet in editor and verify no orphan bullet point renders in template preview.
BUG-009 | src/components/templates/ClassicTemplate.jsx | ClassicTemplate.jsx: 31-56 | Clean contact item separators in Classic header | // Build array of contact elements and render with interspaced dots: const contactItems = [ personal.location, personal.phone && <a key="tel" href={`tel:${personal.phone}`}>{personal.phone}</a>, personal.email && <a key="mail" href={`mailto:${personal.email}`}>{personal.email}</a>, personal.website && <a key="web" href={sanitizeUrl(personal.website)} target="_blank" rel="noreferrer">{formatUrl(personal.website)}</a>, personal.linkedin && <a key="li" href={sanitizeUrl(personal.linkedin)} target="_blank" rel="noreferrer">LinkedIn</a>, personal.github && <a key="gh" href={sanitizeUrl(personal.github)} target="_blank" rel="noreferrer">GitHub</a> ].filter(Boolean); // In JSX: <div className="flex flex-wrap justify-center items-center gap-2 mt-2 text-xs sm:text-sm text-gray-600"> {contactItems.map((item, idx) => ( <React.Fragment key={idx}> {idx > 0 && <span>•</span>} <span>{item}</span> </React.Fragment> ))} </div> | Clear phone/location and check that no orphan bullet appears before LinkedIn.
BUG-010 | src/components/templates/*.jsx | Custom Sections block | Guard against rendering empty custom sections | {customSections && customSections.filter(sec => sec.items && sec.items.length > 0).map((sec) => ( <section key={sec.id}> <h2 className="text-sm font-bold uppercase tracking-wider mb-2 flex items-center gap-2" style={{ color: theme.primary }}> <span className="w-2.5 h-2.5 rounded-full" style={{ backgroundColor: theme.primary }}></span> {sec.title} </h2> ... </section> ))} | Delete all items in custom section; verify section title disappears from preview.

## Traceability Matrix
Requirement ID | Functional Requirement Specification | Associated Test Cases | Execution Result | Linked Defect IDs | Risk Assessment
REQ-NAV-01 | Landing Page presentation and navigation to workspace | TC-NAV-01 to TC-NAV-08 | 100% Passed (8/8) | None | Low
REQ-PER-01 | Personal details input, avatar photo processing and sizing | TC-PER-01 to TC-PER-10 | 80% Passed (8/10) | BUG-007 | Medium (XSS)
REQ-SUM-01 | Summary text editing, char count, and quick inspirations | TC-SUM-01 to TC-SUM-05 | 100% Passed (5/5) | None | Low
REQ-EXP-01 | Work experience management, reordering, and bullets | TC-EXP-01 to TC-EXP-09 | 88.9% Passed (8/9) | BUG-008 | Medium
REQ-EDU-01 | Education history records, honors, and score tracking | TC-EDU-01 to TC-EDU-06 | 100% Passed (6/6) | None | Low
REQ-SKL-01 | Organized skill categories, tag input, and deduplication | TC-SKL-01 to TC-SKL-07 | 100% Passed (7/7) | None | Low
REQ-PRJ-01 | Project showcase with live links and repository URLs | TC-PRJ-01 to TC-PRJ-07 | 71.4% Passed (5/7) | BUG-004 | High (Data Loss)
REQ-CRT-01 | Certifications with issuing authority and credential verification | TC-CRT-01 to TC-CRT-06 | 66.7% Passed (4/6) | BUG-004 | High (Data Loss)
REQ-CST-01 | Custom sections creation, editing, and rendering | TC-CST-01 to TC-CST-06 | 83.3% Passed (5/6) | BUG-010 | Low
REQ-DSG-01 | Multi-template switching, palettes, typography, zoom | TC-DSG-01 to TC-DSG-08 | 75.0% Passed (6/8) | BUG-006, BUG-009 | Medium
REQ-DAT-01 | Local storage caching, JSON export, and backup restoration | TC-DAT-01 to TC-DAT-08 | 75.0% Passed (6/8) | BUG-005, BUG-011 | High (Crash)
REQ-PRN-01 | PDF generation via vector browser print engine | TC-PRN-01 to TC-PRN-05 | 20.0% Passed (1/5) | BUG-001, BUG-002, BUG-003, BUG-012 | Critical